## Slide 1: Bluetooth Android Intern Project -Semester Extension- Gate 1
Blaine Tiernan

## Slide 2: Meeting Agenda
Market Overview
Business Estimates
Risk
Gate 1 Deliverables
  WBS
  MRS
Gate 1 – Bluetooth Android Intern Project

## Slide 3: Market Overview
Market drivers for Android Application w/ Bluetooth
  Estimated 36.7 % of US smartphones are Androids.http://www.statisticbrain.com/android-phone-statistics/
  59% of US tablet owners have Android Tablets. http://www.emarketer.com/Article/With-More-Models-on-Market-How-Tablets-Stacking-Up/1009982
  Android App would keep Technicians from having to carry around a laptop.
  Helps sell Flow Computers.
Bluetooth Android Intern Project

## Slide 4: Market Overview
Competition
  Seeing as that this project was designed as a bonus for the consumer to make communicating and pulling readings from G4 flow computers easier, there is no real competition.
Bluetooth Android Intern Project

## Slide 5: Market Overview
How it works
  User will connect to G4 device through Bluetooth or Wifi to the Android Totalflow Application to gather trending data from G4 device.
Bluetooth Advantages over PCCU
Serial Linkup
  Allows Wireless communication
  Allows phone only communication,
    Laptop no longer necessary
  Can be operated from within the comfort of vehicle
Bluetooth Android Intern Project Technology

## Slide 6: Financial Analysis
Business Case Summary
 | Most Likely | Optimistic | Pessimistic
Time (in Weeks) | 16 | 14 | 18
Cost of Labor (in US Dollars) | 15,859.20 | 13,876.80 | 17,841.60

## Slide 7: Financial Analysis
Risk Summary
Risk Description | Schedule Impact | Scope Impact | Budget Impact | Total Impact | Likelihood Mutliplier | Quantitative Risk Value (1-15) | Status | Mitigation
Device Remember' Function Non-Functional | 3 | 3 | 3 | 9 | 70.00% | 6.3 | Closed | Closed 9/26/13 – Function Fixed
Inexperience w/ Objective C and its Translation from Java | 3 | 3 | 3 | 9 | 100.00% | 9 | Closed | Closed 9/26/13 – Accepted as Stretch scope and will be undertaken only if time permits
G4 Device Unexpectedly Switching from Local to Remote | 4 | 5 | 4 | 13 | 80.00% | 10.4 | In Progress | Scheduled Research – attempt to never disconnect
Write Register Incompatibility with Past Design | 3 | 4 | 3 | 10 | 100.00% | 10 | Open | Suggestion: Ground up Software Rewrite
Bluetooth Successful Connection Inconsistency | 3 | 4 | 3 | 10 | 100.00% | 10 | Open | Suggestion: Ground up Software Rewrite
Register Display Facelift Requires Surplus Manhours | 2 | 3 | 2 | 7 | 80.00% | 5.6 | Open | Suggestion: Ground up Software Rewrite
Android Firmware Incompatibility | 1 | 1 | 1 | 3 | 30.00% | 0.9 | Open | Testing Application for the Most Popular Firmware Releases: 2.3.3 and 4.3

## Slide 8
Main Menu – Page 1

## Slide 9
Wi-Fi Connection – Page 1A

## Slide 10
Bluetooth Connection – Page 1B

## Slide 11: Bluetooth Android Intern Project Gate 1
Gate 1 Deliverables / Milestones
  Work Breakdown Structure (WBS)
  Effort Estimate
  Project Charter (MRS)

## Slide 12: Bluetooth Android Intern Project Gate 2
Gate 2 Deliverables/Milestones :
  Technical Requirements Document
    Detailed product requirements based on Marketing Requirements Specification
    High level software architectural solution
    Traceability back to Marketing Requirements Specification
  Product Development Plan
    Development strategy
    Resource requirements
    Detailed schedule
    Development costs
    Project risks & mitigation plan
    Gate model deviation requests/approval

## Slide 13: Bluetooth Android Intern Project Gate 3
Gate 3 Deliverable/Milestone:
  Software/Physical Design Specification
    Software Component Definition
    Detailed Design Document
    Traceability to Technical Requirements Document

## Slide 14: Bluetooth Android Intern Project Gate 4
Gate 4 Deliverable/Milestone:
  Software
    Code and unit testing
    Integration testing (white box)
    Software design verification testing (white & black box testing)
  System/Quality Testing
    System Test Plan/Procedures (Black box testing – requirements)
    System Automation Test development
  Alpha Unit Build
    Alpha testing is scheduled to start after the 9th of July. Testing will be coordinated by the project manager and the testing customers will be interns Kevin Bright, Nathan Lea, and Trevor Hermosillo.

## Slide 15: Bluetooth Android Intern Project Gate 5
Gate 5 Deliverable/Milestone:
  Software Release

## Slide 16: Bluetooth Android Intern Project Timeline

## Slide 17: Bluetooth Android Intern Project Gate 1
Gate 1 Deliverables / Milestones
  Work Breakdown Structure (WBS)
  Effort Estimate
  Project Charter (MRS)